## Checklist
Counter Detection with a EPS32
Name, Vorname | Alpizar, Dereck |  |  |  | cc: Firmenbetreuer
Matr.-Nr | 7023782 |  |  |  | Projektpartner
Erstprüfer
Checklist
update every day!
No. | Topic | done | date | ETA
First two weeks
1 | read ProjectManagement/BestPractice.pdf | Done | 2022-07-10
2 | fulfill author.xlsx | Done | 14/10/2022
3 | Install TeXLive | Done | 2022-08-10
4 | install TeXStudio | Done | 2022-08-10
5 | install Sumatrapdf | Done | 2022-08-10
6 | configure TeXStudio | Done | 2022-08-10
7 | test template report | Done | 2022-12-10
8 | test template poster | Done | 21/10/2022
9 | test template Presentations/template | Done | 21/10/2022
10 | install doxygen | Done | 24/10/2022
11 | literature research | Done | 28/10/2022
12 | presentation "Literature" | Done | 14/10/2022
13 | write n introduction | Done | 2022-07-11
14 | presentation "Introduction"
15 | project plan | Done | 24/10/2022
16 | fulfill the list "Resulting Objects" | Done | 15/01/2023
17 | presentation "Project Plan"
18 | update project plan | Done | 15/01/2023
19 | update the list "Resulting Objects" | Done | 26/01/2023
20 | presentation "Project Plan" II
21 | rename all tex files along the project plan | Done | 23/10/2022
22 | delete or add additional TeX or Python projects, e.g. Manual | Done | 24/10/2022
23 | update README.md | Done | 24/10/2022
24 | update the checklist | Done | 26/01/2023
Processing the project
25 | code directory structure | Done | 2023-12-01
26 | code data transformation | Done | 14/01/2023
27 | code model generation | Done | 26/01/2023
28 | code esp32 code upload | Done | 28/01/2023
29 | work along the project plan | Done | 30/01/2023
30 | update github every day | Done | 30/01/2023
Final stage
31 | check: all website as pdf-file? | ???
32 | check: all pdfs in the folder Documents? | ???
33 | check: all images okay? | Done | 30/01/2023
34 | check spelling | Done | 30/01/2023
35 | check: poster? | Done | 30/01/2023
36 | print poster | ??? | N/A
37 | check: GitHub project | Done | 30/01/2023
38 | ready minimal one day before deadline | Done | 30/01/2023

## Projekt Plan V1.0 (deut.)
Das Liebesleben der Maikäfer bei Nacht
|  | KW | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | ... | 26 | 27 | ... | 30
|  | lfd. Woche | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | ... | 16 | 17 | ... | 20
TP-Nr. | TP-Name | Dauer
1 | Einarbeitung / Literatur | 2.5
2 | ... | 1
3 | ... | ...
4 |  | 2
5 |  | ...
6
7
8
9
10
11
12
13
14 | Verfassen PA / BT / DA / MT | ...
15 | Durchsicht | 2
16 |  | 1.5
17 | Kolloquium | 1
| Urlaub / Feiertage | [5 empty] | Geburt |  |  | Ostern |  | Pfingsten
| Anmeldung / Abgabe | [7 empty] | 34. März |  |  |  |  | 34. Juli
Besprechungen
PJ = Projekt
| TP = Teilprojekt | [8 empty] | x = f(Studiengang)
Anmeldung
Abgabe
Hermann Meyer
Matr.-Nr. 1112569
7. Sem PVT
Version: 1.3 / 29.02.2025
Persönliche Daten
Vorläufiger Titel
der Arbeit
Nr. des Teilprojektes
(10 - 20 incl. Kolloquium)
Bezeichnung des Teilprojektes
Kalenderwoche des Jahres = zeitl. Lage
Laufende Woche der Arbeit seit Start => Dauer
planbare Ausfallzeiten
(selbst, Partner, Prüfer)
Anmeldetermin = gepl. Abgabetermin
abzgl. x Monate (für BT/DA/MT)
geplanter Abgabetermin
Teilprojekt
Balkenlänge = geschätzte Dauer; kleinste Einheit = 0,5 Wochen
subjektiver Abarbeitungzustand des TP bei korrelierender Besprechung
gepl. Besprechungstermin mit Erstprüfer
Planungsstand des Projektplans (Version, Datum)
spontan + intuitiv geschätzte Dauer des TP;
kleinste Einheit = 0,5 Wochen
Projektplan-Muster für eine Projektarbeit (PA) / Bachelor Thesis (BT) / Diplomarbeit (DA) / Master Thesis (MT)
cc: - Firmen-Betreuer
- PJ-Partner
- Erstprüfer
Empfänger
des PJ-Plans
Plan hier: Bearbeitung wegen Auszeit unterbrechen
Plan hier: Bearbeitung trotz Feiertage fortführen
1
2
2
3
5
4
6
7
8
9
10v
11v

## Project Plan V1.0 Orig (eng.)
The Love Life of Cockchafers at Night
|  | Week of Year | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | ... | 35 | 36 | ... | 39
|  | Project Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | ... | 26 | 27 | ... | 30
SP No. | SP's Title | Duration
1 | Informative activities / literature | 2.5
2 | ... | 1
3 | ... | ...
4 |  | 2
5 |  | ...
6
7
8
9
10
11
12
13
14 | Writing of thesis | ...
15 | First checking through by examiner | 2
16 | Optimization | 1.5
17 | Colloquium | 1
| Vacation / holidays | [5 empty] | Birth |  |  | Easter |  | Pentecost
| Enrolement / Submission | [7 empty] | March 34 |  |  |  |  | July 34
Meetings
SP = Sub-project
x = f(course of study)
Enrolement
Submission
Hermann Meyer
Matr.-Nr. 1112569
7. Sem PVT
Version: 1.0 / 29.02.2025
Personal Data
Preliminary title
of thesis
SP's number
(10 - 20 SPs incl. Colloquium)
SP's title
Week of year
Weeks since start of project => duration
schedulable time outs
(causes: yourself, partners, examiner, ..)
Date of enrolement = scheduled date of submission minus x months
scheduled date of submission
SP
Length of bar = estimated duration; smallest unit = 0.5 week
Actual state of SP's completion at time of corresponding meeting
(subjective estimation)
Scheduled meeting with first examiner
Project plan of (version / date)
Duration of SP estimated in the beginning
(spontaneously and intuitivly)
smallest unit = 0,5 week
Template for Project Plan of Master's Thesis
cc: - Contact person in company
- Project partner
- First examiner
Receivers of this project plan
Scheduled interruption of work
Scheduled to continue work despite of holiday
Colloquium
1
2
2
3
5
4
6
7
8
9
10v
11v

## Project Plan V1.3 (eng.)
Counter Detection with a ESP32
|  | Week of Year | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2
|  | Project Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
SP No. | SP's Title | Duration
1 | Informative activities / literature | 15
2 | Introduction Writing | 6
3 | Domain Writing | 6
4 | Data Mining Alg Writing | 7
5 | KDD research for project | 5
6 | Data selection Writing | 6
7 | Data preprocessing Writing | 6
8 | Data transformation Writing | 6
9 | Data Mining Writing | 7
10 | Interpretation Writing | 7
11 | Validation Writing | 7
12 | Hardware Description Section | 5
13 | Software Description | 5
14 | List Of Materials Required | 4
15 | Manual Preparation | 6
16 | Testing Basic HW Features | 3
17 | Implementation of Data KDD Model | 10
18 | Develop Initial Code for ML Model | 5
19 | Optimize the Model - Python | 4
20 | Convert ML Model to C | 4
21 | Load Working Model in ESP32-CAM | 3
22 | Testing the model behavior with HW | 3
23 | Improving Model with real cases | 4
31 | Result / Conclusion / Next Steps | 12
| Vacation / holidays |  | Counter Detection with a ESP32 48 8: 2022-10-31; Counter Detection with a ESP32 52 12: X-Mas
| Enrolement / Submission |  | Counter Detection with a ESP32 47 7: End of November; Counter Detection with a ESP32 48 8: Report Submission; Counter Detection with a ESP32 1 13: 10th January; Counter Detection with a ESP32 2 14: Final Presentation
Meetings
SP = Sub-project
x = f(course of study)
Dereck Alpizar
Matr.-Nr. 7023782
1. Sem MBIDA
Version: 1.0 / 23.10.2022
Template for Project Plan of Master's Thesis
cc: - Contact person in company: N/A
- Project partner: N/A
- First examiner: Elmar Wings
Nisha Kumari
Matr.-Nr. 7023211
2. Sem MBIDA
Neeranjan Jayamurugan Karthikeyani Matr.-Nr. 7023553
1. Sem MBIDA

## Resulting objects
Counter Detection with a ESP32
Name, Vorname | Neeranjan, Jayamurugan Karthikeyani |  |  | cc: Firmenbetreuer
Matr.-Nr | 7023553 |  |  | Projektpartner
Erstprüfer
List of all Resulting Objects
Subtask | Resulting objects | done | date
Literature Research | List of keywords | Done | 28/10/2022
Literature Research | Brief description of the sources: | Done | 28/10/2022
Update Project's bib file | bib file | Done | 2022-07-11
Update GitHub Daily basis | Review GitHub Activities for User | Done | 30/01/2023
Data | Done in the final report ".\report" on the section "4.1 Database Description" | Done | 2023-04-01
Data Version Control
Structure | Done in the final report ".\report" on the section "1 Introduction" and Files under ".\Code\Basics" | Done | 2023-10-01
Documentation developer : Structure | Done in the final report ".\report" on the section "1 Introduction" | Done | 2022-07-11
Documentation developer : Idea | Done in the final report ".\report" on the section "1.1" | Done | 2022-07-11
Documentation developer : Flow Chart | Done in the final report ".\report" on the "Figure 3.1: KDD process" | Done | 20/11/2022
Meter Counter Digitized | Done in the final report ".\report" on the section "5.1: Meter Counter Digitized" | Done | 26/01/2023
Doxygen | Files under ".\Code\Docs\Doxygen" | Done | 30/01/2023
Monitoring | Done in the final report ".\report" on the section "5.2 Monitoring" | Done | 26/01/2023
Requirements.txt | Files under ".\Code\Docs\requirement.txt" | Done | 30/01/2023
Software Bill of Materials | Files under ".\Code\Docs\sbom.json" | Done | 30/01/2023
program | Files under ".\Code" | Done | 30/01/2023
Programme Flowchart | Done in the final report ".\report" on the "Figure 5.5: Software flowchart" | Done | 26/01/2023
description of important modules : Keras | Done in the final report ".\report" on the section "7.2" | Done | 26/01/2023
description of important modules : Numpy | Done in the final report ".\report" on the section "7.4" | Done | 30/01/2023
description of important modules : Matplotib | Done in the final report ".\report" on the section "7.3" | Done | 25/01/2023
Hardware: Description | Done in the final report ".\report" on the section "5.1.2 Hardware" | Done | 18/11/2022
Hardware: Software | Done in the final report ".\report" on the section "5.1.3 and 5.1.4" | Done | 18/11/2022
Tests | Done in the final report ".\report" on the section "5.1.4 Tests" | Done | 18/11/2022
Development Environment | Done in the final report ".\report" on the section "2.6 Visual Studio Code" | Done | 16/12/2022
Development Environment: First Steps | Files under ".\Code\Basics" | Done | 13/01/2023
poster | Files under ".\Poster" | Done | 25/01/2023
Manual | Files under ".\manual" | Done | 28/01/2023
Documentation: todo/unanswered points/next steps | Done in the final report ".\report" on the section "6: Conclusions / Open Questions" | Done | 28/01/2023
Projectplan-Project (10credits) in Master Course "Business Intelligence and Data Analytics"